## Sheet1
Statement of Work
Company name | Alanand Solutions
SOW Version | 2.4.5
Date Submitted | 2020-05-07
Author | Alanand
ORGANIZATION
Client Name | Chris
Client Phone | (309)550-****
Client Email | chris2@gmail.com
Current Mailing Address | 1010 chrish Avenue, Jai Balayya Street,Ayyagare noone,NY.
Project
Project Name | SQA System for Binami Software Company
Client | chris
Brand | tennis
Begin Data | 2020-01-27
End Data | 2022-03-14
Project Duration | 556
GOALS
Objective | To provide a SQA system which tests the Software Systems
Business | Providing Software Systems
Solution | Software Solutions
Technical | Every Technical Support
Service | Service for 3 Years
Milestones
Estimated Delivery Date | Project Milestone Title
2021-05-10 | Release 1
2021-08-19 | Release 2
2021-11-30 | Release 3
2022-03-11 | Release 4
Standard Adherence
The incremental Model is used so which suits the SQA system to build and modify for every increment
Rate Schedule
Estimated Cost | Delivery Schedule | Description
162735.52 | 2020-03-20 | 1.1 Project Initiation
286971.5 | 2020-09-07 | 1.2 Project Plan
684274.56 | 2021-05-10 | 1.3.1 Release 1
342645.68 | 2021-08-19 | 1.3.2 Release 2
342645.68 | 2021-11-30 | 1.3.3 Release 3
342645.68 | 2022-03-11 | 1.3.4 Release 4
2165753.54 | 2022-03-14 | Overall Project
POINTS OF CONTACT
Name/Title | Contact Info
Project Manager | ****************
Project Manager2 | ****************
Business Terms/Conditions
Duration of Services | 3 years of support
Terms of Payment | Release Wise Payment
Contract Modifications | Will be flexible till 2nd Release
Confidentiality | The information is made confiedntial only to the Project Team
Authorization
Client Signature | Anand Reddy
Client Printed Name | Anand Reddy Sripathi
Client Date | 2020-05-07